# Year 3 virtual exchange plan NL-Italy

## Introduction

The following is a plan of action for the exchanges of Isendoorn year 3 students (14-15 years old) and their Italian counterparts. We want our students to have an international experience despite the current covid-related restrictions that make travel abroad impossible. The goal is for our students to develop themselves as global citizens by working together on global issues. We propose to build upon previous experiences with exchange projects, specifically the experiences with ongoing Erasmus projects.

## About the Erasmus projects (Fiorenzuola en Parma l’Europa)

Last year we were granted an initial extension of the project by one year, resulting in an end date of August 2021. The Dutch National Erasmus Authority has now informed us that another extension is possible (until August 2022). Looking at the projections for the vaccination campaigns throughout Europe, this should allow us to organise exchanges in the school year 2021-2022. With your permission I will file a request for the maximum extension until August 2022 with the Dutch National Authority. You do not have to do anything, when the request for extension is processed you will receive official confirmation from the Italian Erasmus Authority.

Because of the extra extension we do not have to worry about the financial aspects of the Erasmus funds. The Erasmus activities that were cancelled last school year can be part of the programme for next year and once completed we will be able to account for the entire Erasmus budget as planned. As you might have heard, it is possible to use Erasmus funds to cover certain costs of a virtual exchange. However, this requires extra steps to be taken and the rewards are limited. Only 10% of the budget for ‘Learning, Teaching and Training Activities’ can be used, and only for the ‘visiting’ schools. Moreover any money spent on virtual exchanges will mean there is less budget next school year for the exchanges. So I would say it is best not to use this option.

## Virtual project

The general idea of the project is for students to work on a practical solution for a problem in the area of sustainability, environment, healthy lifestyle, cultural heritage and food. After identifying the problem, students work on implementing a solution and evaluating the result. The solution must result in a concrete action (intervention) in their own communities in Italy and the Netherlands. Together the Dutch-Italian groups are responsible for creating their own environmental actions and evaluating the results in their respective communities.

## Communication methods

Based on my own experience I think students can work together using Google Documents/Drive/Classroom as well as video conferencing apps such as Zoom or Microsoft Teams. Another option is to use eTwinning, but I must say I do not have much experience with it. Please let me know if you think it is a good idea to use eTwinning.

## Student groups

Below is an overview of the schools/groups involved and the colleagues that are responsible for coordinating a specific group. For the Isendoorn groups it would all be new students as compared to last year. Next year we will also start with a new group of students.

| Isendoorn | Teacher/tutor | Italian partner school | Teacher/tutor |
| --- | --- | --- | --- |
| 3thn (21 students) 3tvr (30 students) | Tom Jansen op de Haar jht@isendoorn.nl Rick Knops knr@isendoorn.nl | Licea Bertolucci, Parma (19 Alice, 18 Maria) | Alice Bellodi a.bellodi@liceoattiliobertolucci.edu.it Maria Saponaro m.saponaro@liceoattiliobertolucci.edu.it |
| 3tvq (30 students) | Jorien Bönker bkj@isendoorn.nl | Scuola per L’Europa (51) | Mattias van den Eede, Paola, Gerry m.vandeneede@scuolaperleuropa.eu |
| 3tvs (30 students) | Elsbeth Doornbos dnb@isendoorn.nl | Fiorenzuola Mattei (22 Chiara, … Francesca) | Donatella Delmiglio donatella.delmiglio@polomattei.it Chiara joins as well, mixed group. |

## Timeline for the project

I suggest we take around two months for the project (see next page for a more detailed schedule). This gives us some room to adjust plans to different school schedules and vacations, without the project lingering on for too long.

### Suggested planning for virtual project

|  | To do | Who? | Time needed |
| --- | --- | --- | --- |
| Week 5 & 6 February 1-14 | Making student groups (4-5 students per group?) | teachers/tutors | 1 hour |
|  | students prepare vlog about their school/town/etc. students identify environmental challenges in their own community (in Geography class?) | students separately | 0,5 hour 0,5 hour |
| Week 7, 8, 9 Feb. 15 - March 7* | meeting and getting to know each other (on Zoom?), showing vlogs | student groups | 0,5 hour |
| * February 22-28 = Isendoorn vacation | exchange ideas for the project. - What environmental problems do the communities have in common? - What can one country learn from the other? | student groups | 0,5 hour |
|  | make a plan of action to be carried out in both communities | Student groups | 1 hour |
|  | Check plans and guide groups | teachers/tutors | / |
| Week 10, 11, 12 March 8 - 28 | Students carry out plans in their own communities | students separately | between 3-6 hours |
|  | Share results in group | student groups | 1 hour |
| Week 13 & 14 March 29 - April 11 | Make an end product that shows the outcome/results of the project. For example a website/video/newspaper article etc. | Student groups | 1-2 hours |
| Week 14 & 15 March 29 - April 11 | Share results with classmates/rest of school/ parents/ wider community. | Student groups | 1-2 hours |